## page break

Trip: Genesee - Trip 1 - Team 1

Time to travel to first site: 04:33:00

Trip total time: 14:38:00

These locations are stored on google map:

<https://tinyurl.com/y5eku8cg>

…………………………………………………………………………..

Day: 1 (total time needed for the day: 14:38:00)

Team: Alene Onion, self

Lake: 0403ROC0155\_Rockville Lake (class B-epi,hyp; sampleIDs: 2004ROC0S11, NA)

Access location: 42.307894, -78.150332000000006 || Deep Hole: 42.30817548,-78.14973361 || Max Depth: NA

QC Sample to collect: Duplicate

Estimated Sampling Time: 02:00:00 hours || Estimated time to travel to the next site: 01:24:00

Does it need a big boat: No || Motor specifications: No

Access Information: we accessed it here 42.307894, -78.150332 there’s parking and access there

map: NA

…………………………………………………………………………..

Day: 1 (total time needed for the day: 14:38:00)

Team: Alene Onion, self

Lake: 0402GOD0017\_Godfrey Pond (class B-epi,hyp; sampleIDs: 2004GOD0S11, NA)

Access location: 43.029734, -78.111641000000006 || Deep Hole: 43.02852742,-78.11157256 || Max Depth: NA

QC Sample to collect: Equipment Blank

Estimated Sampling Time: 02:30:00 hours || Estimated time to travel to the next site: 00:37:00

Does it need a big boat: No || Motor specifications: No

Access Information: Check in with the poolhouse/store to notify them that we are there.

map: NA

…………………………………………………………………………..

Day: 1 (total time needed for the day: 14:38:00)

ALS Rochester 1565 W Jefferson Rd # 360, Rochester, NY 14623

Estimated 30 min to ship samples at UPS store and no time to travel to the hotel.

Time to next: 03:33:00

## page break

Trip: Genesee - Trip 1 - Team 1

Time to travel to first site: 04:33:00

Trip total time: 14:38:00

These locations are stored on google map:

<https://tinyurl.com/y5eku8cg>

…………………………………………………………………………..

Day: 1 (total time needed for the day: 14:38:00)

Team: Stephanie June, self

Lake: 0403ROC0155\_Rockville Lake (class B-epi,hyp; sampleIDs: 2004ROC0S11, NA)

Access location: 42.307894, -78.150332000000006 || Deep Hole: 42.30817548,-78.14973361 || Max Depth: NA

QC Sample to collect: Duplicate

Estimated Sampling Time: 02:00:00 hours || Estimated time to travel to the next site: 01:24:00

Does it need a big boat: No || Motor specifications: No

Access Information: we accessed it here 42.307894, -78.150332 there’s parking and access there

map: NA

…………………………………………………………………………..

Day: 1 (total time needed for the day: 14:38:00)

Team: Stephanie June, self

Lake: 0402GOD0017\_Godfrey Pond (class B-epi,hyp; sampleIDs: 2004GOD0S11, NA)

Access location: 43.029734, -78.111641000000006 || Deep Hole: 43.02852742,-78.11157256 || Max Depth: NA

QC Sample to collect: Equipment Blank

Estimated Sampling Time: 02:30:00 hours || Estimated time to travel to the next site: 00:37:00

Does it need a big boat: No || Motor specifications: No

Access Information: Check in with the poolhouse/store to notify them that we are there.

map: NA

…………………………………………………………………………..

Day: 1 (total time needed for the day: 14:38:00)

ALS Rochester 1565 W Jefferson Rd # 360, Rochester, NY 14623

Estimated 30 min to ship samples at UPS store and no time to travel to the hotel.

Time to next: 03:33:00