…………………………………………………………………………..

Day: 3 (total time needed for the day: 11:20:00)

Team: Jesse Keltz, Rebecca Gorney

Lake: 1004LCA0270\_Lower Cascade Lake (class A-epi,hypo; sampleIDs: 19LCB029, 19LCB030)

Access location: 44.2259467, -73.8743894 || Deep Hole: 44.227425,-73.872573 || Max Depth: Unknown

QC Sample to collect: none

Estimated Sampling Time: 02:00:00 hours || Estimated time to travel to the next site: 00:00:00

Does it need a big boat: No || Motor specifications: No

Access Information: State land, cartop launch between Upper & LowerÂ

…………………………………………………………………………..

Day: 3 (total time needed for the day: 11:20:00)

Team: Jesse Keltz, Rebecca Gorney

Lake: 1004UCA0271\_Upper Cascade Lake (class A-epi,hypo; sampleIDs: 19LCB031, 19LCB032)

Access location: 44.2255, -73.87498 || Deep Hole: 44.223817,-73.879097 || Max Depth: 9

QC Sample to collect: none

Estimated Sampling Time: 02:00:00 hours || Estimated time to travel to the next site: 00:41:00

Does it need a big boat: No || Motor specifications: No

Access Information: State land, cartop launch between Upper & Lower

…………………………………………………………………………..

Day: 3 (total time needed for the day: 11:20:00)

Team: Jesse Keltz, Rebecca Gorney

Lake: 1005BAR0338\_Bartlett Pond (class A-epi; sampleIDs: 19LCB033, NA)

Access location: 44.1013681, -73.511036 || Deep Hole: 44.1056,-73.51178 || Max Depth: 5

QC Sample to collect: none

Estimated Sampling Time: 02:00:00 hours || Estimated time to travel to the next site: 01:13:00

Does it need a big boat: No || Motor specifications: 1

Access Information: Contact Village of Port Henry/Town of Moriah, <https://www.porthenrymoriah.com/living-here/town-moriah/town-government.Â> \*\*\*Wylie would like us to meet his high school students at the black lake trib sites in July. email the week before